## Task Split
Group | Task | Owner | Notes | Status
Individual | VNet, subnet and private DNS plan (CIDR proposal) | Jag | Raju approves CIDR | Proposed
Individual | Managed identity and RBAC matrix | Jag | Needs Mayur's service-to-resource access list | Proposed
Individual | Gateway choice (App Gateway vs APIM) and cost estimate | Jag | Use free Azure pricing calculator | Proposed
Individual | Resource inventory and naming | Jag |  | Proposed
Individual | Monitoring design | Jag |  | Proposed
Group | Resource groups, basic provisioning, coordination | Raju + Jag | Raju said he will take these | Proposed
Group | Container Apps environment in the VNet | Jag + Mayur + Raju |  | Proposed
Group | Image deploy: ports, env vars, health probes | Mayur | Jag advises | Proposed
Group | Postgres connection and DB migrations | Mayur + Jag |  | Proposed
Group | Service Bus and Blob wiring | Mayur + Jag |  | Proposed
Group | Frontend to API connectivity (auth, CORS) | Mayur + Jag |  | Proposed
Group | End-to-end smoke test | Mayur + QA + Jag |  | Proposed

## Architecture
Type | Item | Owner | Status
Deliverable | Standard Azure microservice deployment architecture draft (v2) with diagram and design notes | Jag | Draft ready; to share in DevOps channel
Scope | Generic standard design, Dev only. Container Apps, private networking, ingress, identity. No Terraform, client-specific or production work yet. | Jag | Per Raju
Design | Public: Static Web Apps + gateway. Internal VNet-integrated Container Apps environment with six services. PostgreSQL via delegated subnet + private DNS. Private endpoints for Blob, Service Bus, Key Vault, ACR, Azure OpenAI, Content Understanding. Managed identity per service. Entra ID for auth. NAT gateway outbound, Bastion for admin, Azure Monitor. | Jag | Draft for review
Decision needed | Gateway: Application Gateway (WAF) vs APIM in the VNet, and SKU for Dev cost | Raju | Open
Decision needed | Premium SKUs for ACR and Service Bus (required for private endpoints): budget OK? | Raju | Open
Decision needed | VNet CIDR and subnet plan (Jag proposes, Raju approves) | Raju | Open
Input needed | Final service names (five or six), ports, which services have ingress | Mayur | Open
Input needed | Two or three frontends (admin, cpp-portal, broker-portal) | Mayur | Open
Input needed | Which services use Postgres, Blob, Service Bus and the AI services | Mayur | Open

## Notes
Type | Note
Support from Raju | Budget access (Jag has none) and Claude account request (may take a day or two).
Plan change | Raju takes resource groups, basic provisioning and coordination; moved to Group tasks.
Plan change | Cost: Jag can use the free Azure pricing calculator.
To confirm | Raju said "five services" once; handover says six. Confirm with Mayur.
Constraint | AI help: generic questions only, no company or customer details. Check the Teams post does not name the company.
Timing | Architecture draft by end of day or tomorrow. Friday is the team's deployment target; Jag has said it is too tight.

## Next Steps
# | Step | Owner | Status
1 | Post the v2 diagram, Teams message and this sheet in the DevOps channel | Jag | Not started
2 | Raju and Jag agree owners for each Individual and Group task | Raju + Jag | Not started
3 | Jag, Raju and Mayur build the networking together | All three | Not started